# Neighbourhood Plan - Steering Group Meeting

# 13th June 2012 – Minutes

## Attending

Cllr Rob Longhurst, Cllr Ben Ingham, Cllr David Atkins, Cllr Richard Eastley, Cllr Pete Acca, Cllr Antony Garret, Don Mildenhall, Helen Dimond, Mark Robertson, Malcolm Lyon, Linda Lyon,

Apologies : Hewyl Parry-Jones

## Recruitment of volunteers for Focus Groups and Steering Group

The Chairman welcomed Mr & Mrs Lyon to the Steering Group

## Focus Groups

MR updated the meeting on Focus Group dates (below).  Participant numbers  were light – all agreed to promote the groups and seek a minimum of 8 per meeting.

Formats had been agreed between MR and the Owners.

| Focus group | Suggested format | Owner |
| --- | --- | --- |
| Housing | Focus Group | RL |
| Infrastructure | Focus Group | AG – 3rd July |
| Environment | Focus Group | HD – 4th July |
| Community | Focus Group | DM – 26th June |
| Target group |  |  |
| Consultation with school children | ‘Mini-version’ of presentation at school | AG – 22nd June |
| Consultation with young parents | Perhaps extension of above to bring parents into the school | AG – 22nd June |
| Consultation with teenagers | Event at youth club – perhaps expanded focus group | Linda Lyon |
| Marines Families | Discussion group organised / facilitated by RMCTC welfare officer | PA |
| Local landowners | Event / discussion to be determined with Richard Eastley | RE |
| Older people | Discussion group organised by TAP | DM to ask Dorothy Livingstone |
| Discussion with shopkeepers | Individual structured questionnaire | DM to do Q’aire; HP-J/PA to run |
| Discussion with other village businesses | (Put emphasis on those which provide services for village, eg Jason Ingham, Miles Freeman, Dave Tyrrell, Chris Barnacle etc) | MP and PA/HP-J |
| ? Old village families | Discussion of issues in group at Globe? | On Hold |
| ? People living beyond A376 | Meeting at Kings ? | David Atkins /Jim Bailey |
| Health & Wellbeing | Presentation | RE to speak to LA – RL to provide transcript of interview with |

## Overall timescale & resources

General acceptance that there will be slippage but also agreement that we need to get the process right and learn the lessons from Dawlish.

- The Neighbourhood Plan MUST interface with the EDDC Local Plan

- There must be a clear audit trail showing how the decisions were reached

- Consultation must be demonstrable

Actions

- RL to get the NP Application form off to EDDC ASAP

- RL to convene a meeting in about 3 weeks time with Mat Dickens – AG, MR and HD to attend

- RL to update the time line and add milestones and critical events – ready for next meeting.

- MR to see if Bob Vicery (Dawlish) could attend our next meeting to impart lessons learned

## Sustainability Appraisal

## Key Issue over which we do not have answers on process or costs - Outstanding

## Documentation of actions + outcomes – who holds and how?

Linda Lyon has accepted this responsibility.

RL to provide disk with current documents.

LL to report back at future meeting on what she wants and some standard formats

## Public statement on costs of NP exercise

Agreed that RL will present a statement at PC Meeting on progress, spend, anticipated costs on 18th June.

## MR Contract

In place.

## EDDC requests for information

- Agreed RL to provide drafts for PC agreement on 18th.

- Meeting to be arranged with landowners and RL, RE and HD to draw up the “preferred development list”.  This to be agreed by the PC and sent to EDDC by end of first week in September.

## Confidentiality

AG to draw up a short statement for all to sign at next meeting.

## Next Meeting

Wednesday 18th July

R Longhurst – Chairman

15/06/2012