# Neighbourhood Plan - Steering Group Meeting

# 20th September 2012 – Minutes

## Attending

Cllr Rob Longhurst, Cllr Ben Ingham, Cllr Richard Eastley, Cllr Antony Garret, Don Mildenhall, Helen Dimond, Mark Robertson, Hewyl Parry-Jones, Cllr Pete Acca, Malcolm Lyon

Appologies :, , Cllr David Atkins, Linda Lyon

## Outstanding Items

| Target group |  |  |
| --- | --- | --- |
| Consultation with school children | ‘Mini-version’ of presentation at school | Completed – LL to send notes to Head for agreement |
| Consultation with young parents | Perhaps extension of above to bring parents into the school | AG – On hold |
| Consultation with teenagers | Event at youth club – perhaps expanded focus group | Linda Lyon |
| Marines Families | Discussion group organised / facilitated by RMCTC welfare officer | PA |
| Older people | Discussion group organised by TAP | DM to ask Dorothy Livingstone |
| Discussion with shopkeepers | Individual structured questionnaire | Completed |
| Discussion with other village businesses | (Put emphasis on those which provide services for village, eg Jason Ingham, Miles Freeman, Dave Tyrrell, Chris Barnacle etc) | Completed |
| ? Old village families | Discussion of issues in group at Globe? | On Hold |
| ? People living beyond A376 | Meeting at Kings ? | David Atkins /Jim Bailey |
| Health & Wellbeing | Presentation | RE to speak to LA |

## Sustainability Appraisal

## Helen Dimond agreed to keep a watching brief and lead this element through a small Sub-Committee.

## HD also agreed to review the Lympstone Village Design Statement (a suggestion from EDDC) via a small sub-committe.

## Documentation of actions + outcomes – who holds and how?

Linda Lyon has accepted this responsibility.

LL to report back at future meeting on what she wants and some standard formats

## Confidentiality

Presented to non-council members to sign (Councillors bound by existing protocols).

## Dinan Way Extension

RL to set up meeting with DCC Highways to understand their current thinking on the primary choice route

## Skeleton Document

Don Mildenhall presented an extensive piece of work on the skeleton document and the associated timeline.

It was agreed:-

- Additional resources were required to complete the writing of the document

  - Structure Editor – Don Mildenhall

  - Editor/Writer – Pete Hardy (RL to approach)

  - Quality Assurance – Antony Garret

  - ANO?

- We should take advantage of the Village Meeting at the end of November to present to the community our progress on the Neighbourhood Plan

- DM/LL/MR should get their ideas together for this and present their findings to the WG on Tuesday 2nd October

- Further funding is required – Ben Ingham to approach EDDC

## Village Boundary Line

RL presented the results of the Village Boundary Line work to date and what was required by EDDC.  The Criteria to be used for assessment were debated and a draft agreed.  It was agreed that at a further meeting on 26th September this work would be progressed in more detail with the intention of producing an objectively assessed and prioritised list of locations for agreement by the Parish Council.

## Next Meeting

As above

R Longhurst – Chairman

02/10/2012